## Dashboard
Audit Readiness Dashboard
Live counts pull from 'Audit Request Log' — update the log and this sheet recalculates automatically.
| Total Requests | Submitted | Overdue | Due Soon | On Track | Completion %
| 8 | 2 | 2 | 2 | 2 | 25%
| Status Breakdown |  |  | Requests by Control Domain
| Submitted | 2 |  | Organizational Controls | 2
| Overdue | 2 |  | People Controls | 1
| Due Soon | 2 |  | Physical Controls | 0
| On Track | 2 |  | Technological Controls | 3
|  |  |  | Access Management | 1
|  |  |  | Business Impact & Risk | 1

## Audit Request Log
Audit Request Log — Compliance & Audit Evidence Tracker
Request ID | Request / Evidence Title | Requesting Team / Auditor | Control Domain | Control Reference | Evidence Owner | Date Requested | Due Date | Status | Effective Status | Days Until Due | Notes
AR-001 | Privileged access review export | Group Audit | Access Management | A.9.2 (ISO 27002) | IAM Lead | 2026-07-21 | 2026-08-01 | In Progress | Due Soon | 5 | Awaiting export from IAM tooling
AR-002 | Incident response runbook v3 | External Audit Firm | Organizational Controls | A.5.24 | SOC Manager | 2026-07-17 | 2026-07-25 | Not Started | Overdue | -2
AR-003 | Vulnerability scan reports Q3 | Group Compliance | Technological Controls | A.8.8 | Threat Mgmt Lead | 2026-07-23 | 2026-08-06 | Not Started | On Track | 10
AR-004 | Change management approvals log | Internal Audit | Technological Controls | A.8.32 | DevSecOps Lead | 2026-07-19 | 2026-07-26 | In Progress | Overdue | -1
AR-005 | Data classification policy sign-off | Group Compliance | Organizational Controls | A.5.12 | Data Governance Lead | 2026-07-07 | 2026-08-16 | Submitted | Submitted | - | Filed in repository
AR-006 | SIEM log retention evidence | External Audit Firm | Technological Controls | A.8.15 | SOC Lead | 2026-07-24 | 2026-07-30 | Submitted | Submitted | -
AR-007 | Business impact analysis report | Internal Audit | Business Impact & Risk | BIA-01 | Resilience Lead | 2026-07-12 | 2026-07-28 | In Progress | Due Soon | 1
AR-008 | Security awareness training records | Group Compliance | People Controls | A.6.3 | HR Security Liaison | 2026-07-20 | 2026-08-11 | Not Started | On Track | 15
Formulas:
Effective Status = IF([Request / Evidence Title]="","",IF([Status]="Submitted","Submitted",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=5,"Due Soon","On Track"))))
Days Until Due = IF([Request / Evidence Title]="","",IF([Status]="Submitted","-",[Due Date]-TODAY()))

## Control Reference
ISO 27001/27002 & COBIT Control-to-Evidence Reference
Control ID | Domain | COBIT Ref | Control Name | Evidence to Request
A.5.1 | Organizational Controls | APO01 | Policies for information security | Board/management-approved security policy document with version history and review dates.
A.5.9 | Organizational Controls | APO03 | Inventory of information and assets | Current asset register export (systems, data classification, owners).
A.5.12 | Organizational Controls | APO03 | Classification of information | Data classification policy sign-off and sample of classified records/labels.
A.5.15 | Organizational Controls | DSS05 | Access control | Access control policy plus periodic access review reports and approvals.
A.5.24 | Organizational Controls | DSS02 | Incident management planning | Incident response plan, roles matrix, and evidence of tabletop exercise.
A.5.30 | Organizational Controls | DSS04 | ICT readiness for business continuity | BCP/DR test results and sign-off from most recent exercise.
A.5.35 | Organizational Controls | MEA04 | Independent review of information security | Latest internal/external audit report and remediation tracker.
A.5.36 | Organizational Controls | MEA03 | Compliance with policies and standards | Compliance self-assessment results and exception register.
A.6.3 | People Controls | APO07 | Security awareness, education and training | Training completion records / LMS export for the audit period.
A.6.6 | People Controls | APO07 | Confidentiality / non-disclosure agreements | Signed NDA templates and sample of executed agreements.
A.7.4 | Physical Controls | DSS01 | Physical security monitoring | Access log exports / CCTV retention confirmation for data center or office.
A.8.2 | Technological Controls | DSS05 | Privileged access rights | Privileged account inventory and quarterly re-certification evidence.
A.8.8 | Technological Controls | BAI03 | Management of technical vulnerabilities | Vulnerability scan reports and remediation SLA tracking export.
A.8.9 | Technological Controls | BAI10 | Configuration management | Baseline configuration standards and configuration drift reports.
A.8.15 | Technological Controls | DSS05 | Logging | SIEM log retention settings and sample log export covering audit period.
A.8.16 | Technological Controls | DSS05 | Monitoring activities | SOC monitoring dashboard screenshots and alert-handling records.
A.8.24 | Technological Controls | DSS05 | Use of cryptography | Encryption standard documentation and key management procedure.
A.8.32 | Technological Controls | BAI06 | Change management | Change request tickets with approvals for a sample of production changes.
A.9.2 (ISO 27002) | Access Management | DSS05 | User access management | Joiner/mover/leaver process evidence and periodic access review sign-off.
BIA-01 | Business Impact & Risk | APO12 | Business impact analysis | Latest BIA report identifying critical processes and recovery time objectives.
RISK-01 | Business Impact & Risk | APO12 | Risk assessment & treatment | Risk register with treatment plans and residual risk sign-off.

## Instructions
How to use this tracker
1) Log every incoming audit request in 'Audit Request Log' as soon as it arrives (row per request).
Fill: Request ID, Title, Requesting Team/Auditor, Control Domain (dropdown), Control Reference,
Evidence Owner, Date Requested, Due Date, Status (dropdown: Not Started / In Progress / Submitted).
2) 'Effective Status' and 'Days Until Due' are formulas — do not type into columns J or K.
They auto-calculate Overdue / Due Soon / On Track / Submitted from the Due Date and Status you enter.
3) Use the 'Control Reference' sheet to look up which evidence artifact an auditor typically wants for a
given ISO 27001/27002 or COBIT control — useful when scoping a new request or briefing an evidence owner.
4) The 'Dashboard' sheet recalculates automatically from the log: total requests, completion rate,
overdue count, and breakdowns by status and control domain, each with a chart.
5) The template supports 30 requests (rows 3–32 on the log). To track more, select row 32, insert rows
below it, and copy the formulas in columns J and K down — then extend the ranges in Dashboard formulas.
Extending into Power BI:
Open Power BI Desktop > Get Data > Excel Workbook > select this file > load the 'Audit Request Log'
and 'Control Reference' tables > build visuals (e.g. overdue trend over time, evidence completion by
requesting team). This keeps the Excel file as the source of truth and Power BI as the reporting layer.
Note: sample rows AR-001 to AR-008 are placeholder data to demonstrate the tracker — replace with real
requests, or delete the sample rows and start logging your own.